## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed)
1 | Pasham Bhuvaneshwari | 2026-01-10 | PDF ingestion failed for large files | Sprint 1 | Pasham Bhuvaneshwari | Functional | Increased file handling limit | 2026-01-10 | Closed
2 | Pasham Bhuvaneshwari | 2026-01-11 | Incorrect chunk size causing overlap | Sprint 1 | Pasham Bhuvaneshwari | Logical | Adjusted chunk size and overlap | 2026-01-11 | Closed
3 | Pasham Bhuvaneshwari | 2026-01-12 | Embeddings not stored in ChromaDB | Sprint 1 | Pasham Bhuvaneshwari | Integration | Fixed storage function | 2026-01-12 | Closed
4 | Pasham Bhuvaneshwari | 2026-01-19 | Irrelevant chunks retrieved | Sprint 2 | Pasham Bhuvaneshwari | Performance | Tuned similarity search | 2026-01-19 | Closed
5 | Pasham Bhuvaneshwari | 2026-01-20 | Groq API timeout error | Sprint 2 | Pasham Bhuvaneshwari | API | Added retry mechanism | 2026-01-20 | Closed
6 | Pasham Bhuvaneshwari | 2026-01-21 | Source citation missing | Sprint 2 | Pasham Bhuvaneshwari | Logical | Updated response format | 2026-01-21 | Closed
7 | Pasham Bhuvaneshwari | 2026-01-27 | Chat history not shown in UI | Sprint 3 | Pasham Bhuvaneshwari | UI | Implemented session handling | 2026-01-27 | Closed
8 | Pasham Bhuvaneshwari | 2026-01-28 | Context lost in multi-turn queries | Sprint 3 | Pasham Bhuvaneshwari | Logical | Added conversation memory | 2026-01-28 | Closed
9 | Pasham Bhuvaneshwari | 2026-02-05 | Deployment dependency errors | Sprint 4 | Pasham Bhuvaneshwari | Environment | Installed required packages | 2026-02-05 | Closed
10 | Pasham Bhuvaneshwari | 2026-02-07 | Slow response for large queries | Sprint 4 | Pasham Bhuvaneshwari | Performance | Optimized retrieval | 2026-02-07 | Closed

## Sheet2
Logical
User Interface
Maintainability
Standards
Others